## Gantt Chart Template
Chongbin Ren project timetable | [27 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | master_project |  |  |  |  | COMPANY NAME
| PROJECT MANAGER | Phil Trinder and Natalia Chechina |  |  |  |  | DATE | [8 empty] | 2019.6.17-2019.9.7
[7 empty] | PHASE ONE | [14 empty] | PHASE ONE | [14 empty] | PHASE ONE | [14 empty] | PHASE ONE
WBS NUMBER | TASK Description | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Experiment
| making sure the topic and context |  | 2019-06-17 | 2019-06-24 | 7 | 100% | bar: WEEK 1 M to WEEK 1 F
| software & hardware install and configuration |  | 2019-06-24 | 2019-07-01 | 7 | 100%
| Reroduce previous experiment with router in simple message |  | 2019-07-01 | 2019-07-11 | 10 | 100%
| Reproduce Issac experiment 7 and measure performance |  | 2019-07-11 | 2019-07-17 | 6 | 80%
| P2P network configuration building |  | 2019-07-18 | 2019-08-01 | 13 | 0%
| P2P network measure |  | 2019-08-02 | 2019-08-05 | 3 | 0%
| Udp network configuration and measurement |  | 2019-08-05 | 2019-08-16 | 11 | 0% | bar: WEEK 9 F
Dissertation
| Background writing and modify |  | 2019-06-24 | 2019-07-15 | 21 | 90%
| Installation and configuration |  | 2019-07-11 | 2019-07-15 | 4 | 0%
| Experiment and design |  | 2019-08-16 | 2019-08-30 | 14 | 0%
| result and anyalyse |  | 2019-08-16 | 2019-08-30 | 14 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET