## Sheet1
NO. WEEK | Date | Task description
1 | 6.17-6.23 | making sure the topic and context
2 | 6.24-6.30 | background draft finished
3 | 7.1-7.7 | system and software configuration
4 | 7.8-7.14 | reprodue Issac experiment with router and pass simple data between ROS
5 | 7.15-7.21 | measuer ROS performance in wifi with router
6 | 7.22-7.28 | p2p configuration and reproduce jamies experiment
7 | 7.29-8.4 | measuer ROS performance with p2p
8 | 8.5-8.11 | TCP and UDP network configuration experiment
9 | 8.12-8.18 | TCP and UDP network performance measure and finish all experiment. Then start write the report instruction and abstract.
10 | 8.19-8.25 | write experiment part and evaluation part
11 | 8.26-9.1 | finish all the part and submit to supervisor to check
12 | 9.2-9.6 | modify report and submit